## Xyrem
Item | Dev | UI
Setup project and make installation based on hellwach and parkinson | 16 | 8
Homepage with paragraphs | 6 | 12
Header | 4 | 6
Footer | 2 | 4
Reference block from helwlach | 2 | 2
Search from Paktuell | 6 | 6
Dockchek | 6 | 6
Content pages & components | 24 | 32
Service modules from aktuell | 4 | 6
Add content | 24
| 94 | 82
Drupal + UI dev | 176
UAT 5% | 8.8
QA 25% | 44
228.8

## US motherhood
| Drupal | UI
Homepage | 6 | 12
Header | 4 | 8
Footer | 3 | 3
Tell your story | 14 | 14
Gallery | 16 | 16
Resource | 16 | 20
Community | 12 | 16
Signup | 8 | 23
Unsubscribe | 2 | 4
Add content | 16
| 97 | 116
Drupal + UI dev | 213
UAT 5% | 10.65
QA 25% | 53.25
276.9